BOARD OR COMMITTEE MEETING

Date:	Public Board Meeting – 11 March 2026	Agenda item: 4.1 / Paper number: CM/03/26/41
Title of paper:	Rebuilding Portfolio Update
Purpose of paper:	For discussion
Executive sponsor:	Arun Chopra – Interim Chief Executive
Accountable Director:	Fiona Dolman – Programme Director
Presenter(s) or lead person:	Fiona Dolman – Programme Director
Summary: / In the last public board meeting in November 2025, we set out our proposal for phase 1 of our rebuilding roadmap and provided an update on the consultation that was currently in progress. Since then, we have set up our rebuilding portfolio and programmes and have delivered several key milestones. This paper sets out the work to date and the immediate actions and next steps.

Programme Structure, Governance and Assurance

The rebuilding portfolio is set up to ensure that we are delivering on three critical elements. The portfolio delivery is overseen by our Programme Director, and the full portfolio and chairing of the portfolio oversight group is undertaken by our Chief Executive, recognising the critical nature of the work that we need to deliver. Each programme within the portfolio has an executive sponsor, the programmes and their sponsors are set out below:
- Rebuilding our regulatory services (Executive Sponsor: Toli Onon, Chief Inspector of Hospitals). This focuses on strengthening our regulatory process, from registration through to assessment and enforcement.
- Rebuilding our organisation (Executive Sponsor: Chris Usher, Interim Deputy Chief Executive). This programme focuses on shaping our organisation to support effective regulation.
- Rebuilding our digital future (Executive Sponsor: Esther Provins, Chief Digital, Data and Registration Officer). This focuses on building the digital and data capability we need with trusted data and services that support our work.

Learning from historical change and transformation programmes, we recognise it is critical that the portfolio complies with Managing Successful Programmes (MSP) standards and has our employee and stakeholder voice embedded into the portfolio through coproduction and also offering critical feedback and engagement as reach milestones.

In December 2025 during private board the Strategic Outline Case (SOC) for the rebuilding portfolio was approved. The SOC allows the rationale and alignment of the portfolio to be clearly set out, and approval for the way forward, enabling us to commence more detailed planning and discovery. We have spent time mapping the recommendations that were received from independent reviews over the previous years into the portfolio, these include recommendations from Penny Dash, Sir Mike Richards, Peter Gill and the Care Provider Alliance. By ensuring the recommendations from the reviews are mapped into the portfolio delivery, in several programmes it is very clear ‘why’ we need to change, and this can allow the work to focus on the more detailed how and when.

Clear governance arrangements are being put in place across all three programmes. The Executive sponsors have been appointed, and Senior Responsible Officers are in place or are onboarding to provide oversight, leadership and accountability and to enable benefits to be fully realised. Programme Boards have now been set up and all had their first meetings in February, providing regular oversight of progress, risks and delivery. A co-design approach for the organisation has been designed and will be rolled out during the spring.
Rebuilding our regulatory services

From 16 October to 11 December 2025, we undertook a public consultation on high level principles for our future approach to provider assessment. The consultation had two areas of focus:
- How we are proposing to develop our frameworks and guidance for assessing providers; and
- How we propose to change our methods for inspecting, assessing and awarding ratings to health and care services
We also sought input during the consultation on our current approach to rating NHS Trusts, and whether we should consider changes.

We have worked through the detailed feedback received from the consultation and in February 2026 board decided some key points that help to take forward the development of the assessment frameworks, beginning with the draft frameworks.

The following points have been agreed:
- We will reintroduce sector-specific assessment frameworks, beginning with four draft frameworks covering:
  - Adult Social Care
  - Mental Health
  - Primary and Community Healthcare
  - Secondary and Specialist Healthcare
- We will reintroduce rating characteristics as of our assessment frameworks
- Change quality statements to a supporting question format
- Remove scoring from our assessment methodology
- Make rating judgements directly at Key Question level.

Next Steps:
- The next stage of this work will be to publish four initial draft frameworks for targeted consultation. These will be draft to offer further opportunities for engagement and feedback, not only on the content of the frameworks but whether the sector split is the correct scope.
- We will also be looking to publish a detailed response to last year’s public consultation, showing what led us to the decisions that we have made to date.

Rebuilding our organisation

At the end of 2025 we integrated our Operations and Regulatory Leadership functions, into sector-specific teams under the four chief inspectors. More recent work has involved establishing the scope of focus for this programme and what the immediate priorities are, things to focus on next and things for the future.

There are several areas across the business that require immediate focus to ensure they are operating effectively to support the business, as well as services where the roles and responsibilities is not as clear as it should be across CQC. This programme aims to address these issues and more, to ensure that our enabling functions are set up in a way to support our regulatory delivery.

Next steps:
The next stage of this work will be to agree the scope of work with the Programme Board that has been established, to recruit a programme manager to lead the work and to set up ways of working to sequence and deliver the programme.

Rebuilding our Digital Future

Following the approval of the SoC we have onboarded an interim IT supplier to enable us to deliver the initial discovery phases of our plan, while we procure a longer-term strategic IT partner to start at the end of Quarter 1 or beginning of Quarter 2 2026/27. During this initial discovery phase we are developing three proofs of concept: assessment, registration and our enterprise data platform. These are small-scales proofs of concept to test that our our architectural approach and system configuration is sound before moving to full delivery.

Whilst the longer-term digital transformation work is underway, we put in place a multi disciplinary team with representation from all key regulatory functions to oversee the delivery of quick and effective tactical solutions to the challenges we currently face with the regulatory platform. This team reviewed over 3600 requests for change that had been received and have consolidated and agreed 44 tactical actions to improve current challenges and mitigate current risks. A number of fixes have already been delivered including some improvements to the factual accuracy process, with more planned. This work has also included delivering regulatory platform refresher training sessions for operational colleagues and publishing streamlined guidance.

Alongside our tactical solutions we have been exploring the use of artificial intelligence (AI) and automation to support productivity, through some early pilots. An AI chatbot is being piloted to help navigate guidance quickly and Copilot is being trialled to help speed up report writing. Working with a number of providers, a pilot of Ambient Voice Technology to capture information quickly during inspections is underway, with appropriate consent processes in place.

Next Steps:
From spring we will be using the learning from the proof-of-concept work undertaken in the discovery phase, we will co-design how we develop our new assessment technology, our regulatory data requirements and strengthening our data platform architecture.