No	Ref	Subject	Action Required	Owner	Meeting Date	Date Due	Progress / Comment	Date / Completed	Status
1	CM/11/24/52	Response to Ofsted Inquest – Protecting CQC colleague and Provider Welfare - Learning Resources	The paper was due to be presented to the Board in November 2024 but was deferred for consideration at the March meeting.	Chris Dzikiti	27/11/24	24/09/25	For consideration at the November 2025 meeting	Deferred to Nov. 2025 / Removed from agenda as superseded by the assessment framework consultation
2	CM/06/25/34	Dementia Strategy & Independent Voice	Submit workplan to ET for approval. Aim to release final statutory guidance during Dementia Action Week in May 2026.	Chris Badger / Stefan Kallee/ / Jo Wallace	25/06/25	May 2026	ET has agreed the workplan in principle pending a review of the timelines to avoid confusion with the assessment framework timelines, and exploration of any relevant NHS plans.

Status key:
Red – overdue Geen - on track Blue – Complete or propose to close